## Requirements
Requirements
Document | Completion Status | Name(s) | Link | Status
Executive Summary | Completed | Kevin Vu, Osman Khan
Stakeholder Model | Completed | Osman Khan
Goal Model | Completed | Anthony Dawson
System Vision | Completed | Gustavo Cisneros
Use Cases | Completed | Gustavo Cisneros, Kevin Vu, Anthony Dawson, Osman Khan, Jose Vasquez
Functional, Non Functional Requirements | Completed | Kevin Vu |  | Constraints still need revision
Use Case 1 - View Splash screen | Completed | Kevin Vu
Use Case 2 - Creating an account | Completed | Kevin Vu
Use Case 3 - Login | Completed | Kevin Vu
Use Case 4 - View Home Menu | Completed | Osman Khan
Use Case 5 - Search for parts with prices, features, etc | Completed | Gustavo Cisneros
Use Case 6 - Managing Budget of List Parts | Completed | Gustavo Cisneros
Use Case 7 - Cloud Database: User Login Information | Completed | Gustavo Cisneros
Use Case 8 - Cloud Database Storage: PC Component Information | Completed | Gustavo Cisneros
Use Case 9 - Product Alert Sign Up | Completed | Jose Vasquez
Use Case 10 - Push Notification | Completed | Jose Vasquez
Use Case 11 - Permissions | Completed | Jose Vasquez
Use Case 12 - Component Barcode Scan | Completed | Jose Vasquez
Use Case 13 - View Component Reviews | Completed | Jose Vasquez
Use Case 14 - View Component Comparison | Completed | Kevin Vu
Use Case 15 - Graphs for Price History | Completed | Osman Khan
Use Case 16 - Suggest Build | Completed | Osman Khan
Use Case 17 - PC Information Page | Completed | Gustavo Cisneros
Use Case 18 - Build Guide | Completed | Anthony Dawson
Usage Model | Completed | Osman Khan | Usage Model Diagram

## Design Specifications
Design Specification ¦ Draw IO Diagrams ¦ Design Presentation
Document | Completion Status | Name(s) | Link | Status
Activity Diagrams
Use Case 1 - View Splash screen | Incomplete
Use Case 2 - Creating an account | Incomplete
Use Case 3 - Login | Incomplete
Use Case 4 - View Home Menu | Incomplete
Use Case 5 - Search for parts with prices, features, etc | Complete | Big Pimpin
Use Case 6 - Managing Compatibility and Budget of List Parts | Its done bruh | Anthony Dawson
Use Case 7 - Cloud Database: User Login Information | Incomplete
Use Case 8 - Cloud Database Storage: PC Component Information | Incomplete
Use Case 9 - Product Alert Sign Up | Incomplete
Use Case 10 - Push Notification | Incomplete
Use Case 11 - Permissions | Incomplete
Use Case 12 - Component Barcode Scan | Incomplete
Use Case 13 - View Component Reviews | Incomplete
Use Case 14 - View Component Comparison | Complete | Kevin Vu
Use Case 15 - Graphs for Price History | Incomplete
Use Case 16 - Suggest Build | Complete | Jose Vasquez
Use Case 17 - PC Information Page | Complete | Osman Khan
Use Case 18 - Build Guide | Incomplete
Site Maps | Incomplete
Class Diagram | Incomplete

## Environment
Language | Dart, Flutter
IDE | Android Studio
GitHub | Plugin in Android Studio
Database | Firebase | Setup tables

## Testing
Unit Level | Quality | Use Cases #s | Kevin
Sign Up
Login
Search for Parts
Compatitibility
Info page
Module Level |  |  | Anthony
User Login & Registration
Search Parts
Part Info Page
Build PC Page
Integration Level |  |  | Jose
Google Authentication
FireStore Database
Webscraper
Android Compatibilty
System Level |  |  | Big Pimpin
Acceptance Level |  |  | Osman
Register
Login
Search For Parts
Select a PC Info Page
Review PC Part